## This Week
TYRO — Weekly Status (FIT5230, Theme 2 Dark)
HOW TO USE: update this tab once a week, together, in 5 minutes. Fill the yellow cells. The one question that matters is column E — if Nissa is blocked, nothing else on this sheet counts. ⚠️ This is NOT your M4 log: that one is individual and private. Keep your own.
Week | Dates | Echo — research & strategy | Nissa — implementation | ⚠️ Blocked on / waiting for | Closed out?
W2 | 3–9 Aug | Feasibility smoke test ✅ · plan written ✅ · tutor email sent ✅ | Read the smoke-test notebook end to end |  | Yes
W3 | 10–16 Aug | Read PhotoGuard §3 (encoder attack). Write the 4-cell spec for M1. | Port PhotoGuard PGD loop to diffusers 0.39. Produce protected.png.
W4 | 17–23 Aug | Draft M1 Ed post + the Laundromat challenge. | Cells 3–4: edit protected vs clean (same seed) + JPEG-75 recovery.
W5 | 24–30 Aug | M1 DUE 28 Aug — post to Ed, Colab link, Moodle PDF. | Notebook saved WITH outputs showing. Versions pinned.
W6 | 31 Aug–6 Sep | Read other teams' M1 posts. Leave 2–3 substantive replies. | Purification sweep harness: JPEG q, blur σ, bit-depth, upscale↔downscale.
W7 | 7–13 Sep | Decide the 50-image test set + which metrics we report. | Run the sweep. Write results to CSV as you go.
W8 | 14–20 Sep | M2 DUE 18 Sep — results, trade-off curve, target declared. | Base code released + plots.
W9 | 21–27 Sep | Pick a Light team's defense to attack. Log what they do about it. | DiffPure: noise at timestep t, denoise with SD.
W10 | 28 Sep–4 Oct | INDIVIDUAL: FFT analysis → targeted low-pass filter. | INDIVIDUAL: model-mismatch attack (different VAE).
W11 | 5–11 Oct | Sketch both M4 demos now (EOT loop + switch-sides defense). 9% lives here. | Same — your own version, separately.
W12 | 12–18 Oct | Slides + rehearse to 15:00 with a timer. | Final Colab tidy: no local paths, versions pinned, outputs saved.
W13 | 19–25 Oct | M3 DUE 22 Oct — present. | Final notebook submitted.
W14 | 26 Oct–2 Nov | M4 DUE 2 Nov — individual report, IEEE template, Overleaf. | Same — written alone.

## Results Log
TYRO — Results Log (one row = one experiment run)
HOW TO USE: Nissa adds one row every time an experiment produces a number. A result with no seed and no version numbers is an anecdote, not a result — fill those columns or the row is worthless. Row 5 is a worked example: overwrite it or delete it once you have real runs. This tab becomes the M2 results table with almost no rewriting.
Run ID | Date | Who ran it | Image set | Defense applied | Defense ε / strength | Purification | Purification setting | Seed | torch | diffusers | Edit instruction | CLIP ↑ (edit worked) | LPIPS ↓ (fidelity) | PSNR dB ↑ | Verdict / what we learned
R001 | 2026-08-20 | Nissa | example.jpg (single) | PhotoGuard encoder | 8/255 | None | — | 42 | 2.11.0+cu128 | 0.39.0 | make it a snowy winter scene | 0.21 | 0.42 | 18.7 | EXAMPLE ROW — delete me. Defense holds: output is garbled, CLIP collapses vs clean baseline.

## Deadlines
TYRO — Deadlines
Days left recalculates automatically. Negative means it is behind you.
Milestone | What is actually due | Weight | Due date | Days left | Who owns submission | Status
Registration | Tutor email — team, theme, side | — | 2026-08-21 | 14 | Echo | Done
M1 | Ed post + Colab link + Moodle PDF | 2% | 2026-08-28 | 21 | Echo | Not started
M2 | Results, demos, base code, target declared | 8% | 2026-09-18 | 42 | Both | Not started
M3 | 15-min presentation + final Colab (11% individual) | 25% | 2026-10-22 | 76 | Both | Not started
M4 | Individual report, IEEE template — written alone | 15% | 2026-11-02 | 87 | Each alone | Not started
Total assessed by this project |  | 50%
Of which assessed on you INDIVIDUALLY, not as a team: 26 of 50 marks. Your contributions must be distinguishable.
Formulas:
Days left = [Due date]-TODAY()